## Slide 1: Project Charter VC Nutrifoods

## Slide 2
Project Analysis
Project Overview
Purpose
Project Objective
Scope
Key Deliverables
Development and implementation of an automated Human Capital Management (HCM) dashboard
Automating the HCM dashboard will improve data accuracy, provide real-time insights, and enhance decision-making capabilities.
Create and implement an automated HCM dashboard by August 31, 2024.
Ensure daily automated updates and accurate real-time reporting.
Provide actionable insights on labor contribution and attendance.
Design and development of the automated HCM dashboard.
Alignment on data pipeline from Excel and Google Sheets.
Setup of scheduled data refreshes.
User training and support.
Requirements specification document.
Automated HCM dashboard.
Integration with current data sources (Excel and Google Sheets).
Scheduled data refresh setup.

## Slide 3
Project Team
Management Objectives
Project Objectives
Principal Consultant
Schedules
Tasks
Resources
Business Intelligence Analyst
Junior Analyst
Project Manager

## Slide 4
Schedule and Budget
Project Kickoff: June 1, 2024
Requirements Gathering: June 1 - June 15, 2024
Design Phase: June 16 - June 30, 2024
Development Phase: July 1 - July 31, 2024
Testing Phase: August 1 - August 15, 2024
User Training: August 16 - August 25, 2024
Project Completion: August 31, 2024
Principal Consultant- 20 hours at 15,000
Business Intelligence Analyst- 20 hours at 15,000
Junior Analyst- 90 hours at 18,000

## Slide 5
Inputs for Scheduled Refresh
Current Day's Attendance Marked in ERP:
  Deadline: By 6:00 PM every day.
Responsible for Downloading the Excel File:
  Person: HR Analyst.
Expected Time for Excel File Availability:
  Time: By 7:00 PM every day.
Dashboard Viewing Time:
  Time: Dashboard available for review by 8:00 PM every day.
Dashboard Users:
  Primary User: Vamsi
  Additional Users: HR Team, Operations Managers
Dashboard Insights and Filters
Insights Provided:
  Contribution of labor via Village, Auto Drivers, and Location.
  Metrics: Number and percentage of total, day-on-day growth/decline, week-on-week growth/decline, total attendance per day, per week, per month, per quarter.
Filters:
  Location
  Village
  Shift
  Auto Drivers

## Slide 6
Future Dashboard Required
  This dashboard will track and report the status and frequency of employee top-ups, providing insights into how often and how much additional labor or resources are required to meet operational demands.
Top Up Dashboard:
Performance Management Dashboard
Employee/Labor Efficiency Dashboard:
This dashboard will analyze and present data on individual and group productivity, highlighting areas of high and low efficiency. It will help identify trends, enabling better workforce management and optimization of labor resources.
  This dashboard will monitor and evaluate employee performance metrics, such as key performance indicators (KPIs), goals, and targets. It will support performance reviews, identify high performers, and address areas needing improvement.

## Slide 7: Thank You