## AGOS-Ghanisht
Sr.No | Intervention/ Tasks | Apr |  |  |  | May |  |  |  | Jun
|  | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4
1 | Implementation of Weekly and Daily dashboard
1.1 | Understand the requirement and define the KPIs to be included in Daily and Weekly Dashboard | bar: Jun Wk1 to Jun Wk2
1.2 | Create a dashboard and discuss the same with management | bar: Jun Wk1 to Jun Wk2
1.3 | Finalisation and implementation of Dashboard | bar: Jun Wk1 to Jun Wk3
2 | Proper monthly Management Information System
2.1 | Create and improvise the MIS to include the cash flow and reconciliation with the books | bar: Apr Wk3 to Apr Wk4; May Wk3 to May Wk4
2.2 | Creation of monthly business performance deck and implementation of the same | bar: Apr Wk4 to May Wk4
2.3 | Drive and implement the monthly performance review with the key stakeholders | bar: May Wk4 to Jun Wk2
3 | Payment Mechanism System
3.1 | Understand the current process and controls for Payment | bar: May Wk4 to Jun Wk1
3.2 | Create a Proper system and control for payment mechanism | bar: Jun Wk1 to Jun Wk3
3.3 | Implement proper process and control for making payments | bar: Jun Wk1 to Jun Wk3
4 | Financial Processes
4.1 | SOPs for Cash | bar: Jun Wk1 to Jun Wk4
5 | Debtor Mangement Syatem
5.1 | Prepare tracker from trade receivables with aging schedule | bar: May Wk3 to Jun Wk1
5.2 | Drive and implement of tracker and streamline the process of collection | bar: Jun Wk1 to Jun Wk2
6 | Other deliveries
6.1 | Renegotiation with CMACGM and finalisation of quote | bar: Apr Wk3 to Apr Wk4
6.2 | Workings done for 3 scenerios- without ACS, Inditex and ACS & Inditex | bar: Apr Wk1 to Apr Wk2
6.3 | Working on Cash flow since inception and understand the utlisation of fund | bar: May Wk1 to May Wk2
6.4 | Wealth management | bar: Jun Wk1 to Jun Wk4

## Incertech-Ghanisht (hidden)
INCERTECH - CFO Services Plan
Focus Area | Sl No | Task | November | December | January | February | March
Diagnostic and Baseline Assessment | 1 | Onboarding the client | [5 empty] | Completed
| 2 | Discovery Visit Client place and understand client business, people, policies and processes | [5 empty] | Planned
| 3 | Diagnostic Prepare a Diagnostic report based on the Discovery and share it with the client | [5 empty] | In process
| 4 | 90 Days Plan Prepare the plan for the next 90 days showing a clear picture | [5 empty] | Delayed
| 5 | Conduct the Finance baseline assessment along with Finance team and highlight gap areas if any
| 6 | Review and analyse existing Financials for growth tends and key financial ratios
| 7 | Market and competitor Analysis
Business Strategy (2024-2027) & Organizational Goals | 1 | Strategy Session with Founders and key management team
| 1.1 | Discuss, brainstorm and finalize the winning aspiration for the strategy period
| 1.2 | Discuss, brainstorm and finalize the Go to market strategy i.e
| 1.2.1 | Where to play - Geography, Industry, Customer, channels etc
| 1.2.2 | How to win in the defined markets
| 1.3 | Discuss and define the capabilities required for winning - resources, funds, tools, technology etc
| 1.4 | Brainstorm on the product strategy and international expansion
| 2 | Define business critical goals/KPIs and KRAs to achieve the winning aspirations
| 3 | Scripting Organisational Goals for 2024.
| 4 | Yearly Financial Model (FY 2024-27)
Annual Operating Plan 2024-25 | 1 | Discuss and align on yearly targets for key financial deliverables i.e.
| 1.1 | Revenue for different markets, industry, customer, channels
| 1.2 | Gross margins for different markets, industry, customer and channels
| 1.3 | Direct costs in terms of people, tools, technology based on Org structure defined
| 1.4 | Salary for different skill sets, increments etc
| 1.5 | Other Fixed Costs and optimization targets for controllable fixed costs
| 1.6 | Sales and marketing costs in different markets and in line with the growth in topline
| 1.7 | Understand the aspirations for International expansions and estimate costs associated with it
| 1.8 | Evaluate and estimate the capex requirements
| 1.9 | Evaluate, estimate and optimize DSO, DPO and other working capital assumptions
| 2 | Evaluate funding requirements and define the appropriate capital structure - debt and equity
| 3 | Benchmark with the competition on key financial numbers and ratios
| 4 | Finalize all key assumptions and create the financials - PL, BS and Cashflow
| 5 | Compute Unit Economics
| 7 | Deliver the final financial plan
Costing and Pricing Strategy | 1 | Understand the product, business and manufacturing process
| 1.1 | Gatheirng data and information related to purchase, BOM, cost sheet or any other documents maintained
| 1.2 | Understanding the elements of cost for making and selling the product
| 1.3 | Guiding and helping in apportionment and allocation of Direct anf Indirect costs
| 1.4 | Finalisation of costing template
| 1.5 | Guiding on process used to define the price of the products
| 1.6 | Finalising the pricing template
| 1.7 | Template on Margin Analysis- Actual v/s Standard
Additional Deliveries | 1 | Support in increasing the working capital by creating project plan and meeting with the Banker
| 1.1 | Support in HSE understanding for RIL
| 1.2 | Support in creating the orgnaisation chart
| 1.3 | Creation of Project plan sheet to monitor the operational performance
| 1.4 | Support in entering into partnership model in Gulf conutries
| 1.5 | Support in Proper accounting
| 1.6 | Support in entering into partnership model in South Africa

## Vervali-Hina
Vervali Systems
Sr.No | Area | 2024-04-24 |  |  |  | 2024-05-24 |  |  |  | 2024-06-24
|  | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4
1 | Organisational Goal under Balanced score Card
1.1 | Creation of Organisation Goal | [12 empty] | Completed
| - From financial perspective | [12 empty] | Planned | bar: 2024-04-24 Wk1 to 2024-04-24 Wk2
| - From Customer perspective | [12 empty] | In process | bar: 2024-04-24 Wk1 to 2024-04-24 Wk2
| - From Internal Processes perspective | [12 empty] | Delayed | bar: 2024-04-24 Wk1 to 2024-04-24 Wk2
- From Learning & Growth perspective | bar: 2024-04-24 Wk1 to 2024-04-24 Wk2
1.2 | Discussion and finalisation with the Management | bar: 2024-04-24 Wk2
2 | Annual Operating Plan Implementation
2.1 | - Set clear and measurable Organisation objective aligned with AOP | bar: 2024-04-24 Wk3
2.2 | - Communication to the functional heads and alignment with their individual goal sheets | bar: 2024-04-24 Wk3
2.3 | - Set targets and Budgets for each department and business units | bar: 2024-04-24 Wk4
2.4 | - Allocate Budgets to individual departments | bar: 2024-04-24 Wk4
2.5 | - Align Capability building Budgets with the respective functions | bar: 2024-04-24 Wk4
2.6 | - AOP refresh at the end of quarter (if required) | bar: 2024-06-24 Wk4
3 | Management Information Systems
3.1 | Submission of Monthly Business Deck | bar: 2024-04-24 Wk2; 2024-05-24 Wk2; 2024-06-24 Wk2
3.2 | Project Wise Costing and Profitability working | bar: 2024-04-24 Wk2; 2024-05-24 Wk2; 2024-06-24 Wk2
4 | Management Routines Implementation
4.1 | Fornight Call with the Leadership team with clear actionables | bar: 2024-04-24 Wk4; 2024-05-24 Wk4; 2024-06-24 Wk4
4.2 | Monthly Review with all functions | bar: 2024-05-24 Wk1; 2024-06-24 Wk1
4.3 | Monthly Business Review | bar: 2024-04-24 Wk2; 2024-05-24 Wk2; 2024-06-24 Wk2
5 | Other Deliveries
5.1 | Work towards ESOP; financial model and valuation
5.2

## SL7-Hina
- CFO Services Plan
Focus Area | Sl No | Task | April |  |  |  | May |  |  |  | June
|  |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4
Weekly Dashboard Monthly Closing Activity and Performance Review | 1 | Weekly Dashboard submission by every Tuesday of nect week | [12 empty] | Completed
| 2 | Drive timely closure of books | [12 empty] | Planned
| 3 | Preparation of Monthly Business Review Deck | [12 empty] | In process
| 4 | Monthly Business Review with the founder in the first week of every month
Cash Flow and Wealth Management | 1 | Monitoring the returns on investment on weekly basis to achieve the target of 8% p.a
| 2 | Quarterly review with the wealth advisor | bar: May Wk 1
| 3 | Cash flow forecasting and monitoring the collections through weekly cadence calls
Compliances | 1 | Timely Delivery of Compliance Checklist with Zero Non Compliance on a monthly basis
| 2 | Accurate calculation and timely payment of advance tax
| 3 | US Compliance- Annual and Monthly
Financial Processes | 1 | Pricing Strategy | bar: May Wk 1 to May Wk 4
| 2 | ROI on all marketing spends
Additional Deliverables
Management routines with Praveen

## Balaji-Shudhanshu
Sr.No | Area | Task | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
1 | Inventory optimization | Inventory reconciliation and compiling Non-moving items across multiple units.
2 |  | Monitoring non-moving items across units and implementing disposal procedures along with timelines
3 | Monthly MIS Update & deck | Monthly update: PnL, CFS, BS on MoM basis, followed by consolidated MIS.
4 |  | Creation of Monthly Performance deck for all units
5 |  | Monitoring Major KPI, Variance Analysis
6 |  | Reconciliation of outstanding amounts in all the branches.
7 | Annual Event | Review of last year's business performance, highlighting constraints with the sales, production, and accounts teams, and proposing a way forward.
8 |  | Drafting meeting minutes and highlighting forward-thinking suggestions.
9 | Sales & Production planning and Alignments | Annual Operating Plan (AOP) Discussion with Management
10 |  | Detailed planning for major SKUs in volume terms for production across all units.
11 |  | Aligning production with sales targets for each sales region.
12 | Rolling forecast and AOP Update | Update the Annual Operating Plan (AOP) for each business unit in accordance with the revised sales and production targets for the first and second quarters.
13 | Petty cash monitoring protocol. | Analyzing significant petty cash outflows and mitigating potential leakages through effective measures.
14 |  | Implementing a standardized procedure for cash disbursements and payments within the business.
15 | Brand building and marketing analysis. | Analyzing new sales channel of D2C and modern trade sales segment with a cost-benefit analysis for marketing and sales.
16 | Inventory Management | Updating BoM of Major Products and Contribution Margin workings as per new BoM
17 |  | Ranchi Unit Inventory Analysis and Review
18 |  | Implement a weekly update of material issues to production, including weekly adjustments and ensuring Bill of Materials (BoM) accuracy in line with prevailing trends.
19 |  | Develop Sops for Inventory dispatch procedures
20 | Cost Optimizations | Conducting a comparative cost analysis and benefits evaluation between bag packaging and carton box packaging.
21 |  | Computation of yields at the plant level to optimize and enhance operational efficiency.
22 |  | Closely monitoring major P&L items for effective operational cost reduction.
23 |  | Analyzing slow-moving items at the Ranchi Plant and formulating a production plan based on historical demand patterns.

## CA-Hina
| W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
Finalisation of MIS for FY 23-24 and review the same
Drive closure of books and | bar: W2 to W4
Gather all the informations from the account team | bar: W4
Create MIS for the FY including PnL, BS and Cash flow | bar: W4
Implementation of Record to report SOP | bar: W5 to W8
Management Information Systems
Submission of Monthly Business Deck | bar: W8 to W10
Monthly Business Review | bar: W8 to W10
Project Wise Costing and Profitability working | bar: W8 to W10
Compliance Checklist | bar: W4 to W5
Others
Marketing- monitoring the leads and conversion through participation in the calls | bar: W11 to W13
Monitoring the lost of billing due to leaves and holidays on a monthly basis | [13 empty] | Discussion happened around it | bar: W11 to W13
Finalisation of Incentive for new Sales Head | bar: W1 to W2

## Tataria-Ghanisht
Sr.No | Intervention/ Tasks | Apr |  |  |  | May |  |  |  | Jun
|  | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4
1 | Improvisation and Implementation of Weekly dashboard for
1.1 | - Ligno Industries | bar: Apr Wk1 to Apr Wk3
1.2 | - Tataria Living | bar: Apr Wk3 to May Wk1
2 | Cash Flow Forecasting and Management
2.1 | - Ligno Industries | bar: Apr Wk3 to Apr Wk4; Jun Wk3
2.2 | - Tataria Living | bar: Apr Wk4; Jun Wk3
2.3 | - Tataria Hardware | bar: Apr Wk3 to Apr Wk4; Jun Wk3
3 | Proper monthly Management Information System
3.1 | - Ligno Industries | bar: Jun Wk2 to Jun Wk3
3.2 | - Tataria Living | bar: Jun Wk2 to Jun Wk3
3.3 | - Tataria Hardware | bar: May Wk1 to May Wk3; Jun Wk2 to Jun Wk3
4 | Drive the Monthly Business Performance review for:
4.1 | - Ligno Industries | bar: Jun Wk2 to Jun Wk3
4.2 | - Tataria Living | bar: Jun Wk2 to Jun Wk3
4.3 | - Tataria Hardware | bar: May Wk2 to May Wk3; Jun Wk2 to Jun Wk3
5 | Standard Operating Procedure
5.1 | Procure to Pay SOP for Ligno Industries | bar: Jun Wk1 to Jun Wk4
5.2 | Drive the processes of Inventory forecasting in Hardware | bar: Jun Wk1 to Jun Wk4

## First Sportz-Vivek
First Sportz Media |  | Business Consulting
S.No. | Interface / Tasks | October | November | December | January | Completed
1 | Baseline Assessment |  |  |  |  | Yet to complete
1.1 | Onboarding the client
1.2 | Discovery understand client business, people, policies and processes
1.3 | Diagnostic Prepare a Diagnostic report based on the Discovery and share it with the client
1.4 | 90 Days Plan Prepare the plan for the next 90 days showing a clear picture
2 | Process and Finance Due Diligence
2.1 | Due Diligence of financial system to remove inefficiencies in the operating activities
2.2 | Preparation of Pitch deck for growth
3 | Cash Flow forecasting and management
3.1 | Cash flow forecasting (to anticipate any potential shortfalls or surpluses)
3.2 | Monthly Cash flow forecasting and management
3.3 | Track the actual cash inflow and outflow against the forecasted no.
3.4 | Receivable management through well defined follow up system
3.5 | Review the payment terms with vendor and suggest improvements
4 | Quarterly Business Review
4.1 | Preparation of Business Model for 5 years MoM basis for growth
4.2 | Review the performance with the management
5 | Costing and Profitability Template
5.1 | Understanding the elements of cost for making and selling the product
5.2 | Guiding and helping in apportionment and allocation of Direct and Indirect costs
5.3 | Valuation based on future cash flow and business potential
5.4 | Strategy session on draft valuation report and finalisation
5.5 | Finalisation of Pricing template
5.6 | Suggesting on areas (if any) where cost control can be done
5.7 | GTM Strategy
6 | Adhoc Points
6.1 | Strategy session on where to play and Finalisation on sales target
6.2 | Collection SOP

## Motivus-Vivek
Motivus |  | CFO Services
S.No. | Interface / Tasks | October | November | December | January | Completed
1 | Baseline Assessment |  |  |  |  | Yet to complete
1.1 | Onboarding the client
1.2 | Discovery Visit Client place and understand client business, people, policies and processes
1.3 | Diagnostic Prepare a Diagnostic report based on the Discovery and share it with the client
1.4 | 90 Days Plan Prepare the plan for the next 90 days showing a clear picture
2 | Process and Finance Due Diligence
2.1 | Due Diligence of financial system to remove inefficiencies in the operating activities
2.2 | Strategy to Profitability
3 | Cash Flow forecasting and management
3.1 | Cash flow forecasting (to anticipate any potential shortfalls or surpluses)
3.2 | Monthly Cash flow forecasting and management
3.3 | Track the actual cash inflow and outflow against the forecasted no.
3.4 | Receivable management through well defined follow up system
3.5 | Review the payment terms with vendor and suggest improvements
4 | Quarterly Business Review
4.1 | Preparation of Business Model for 5 years MoM basis for growth
4.2 | Review the performance with the management
5 | Costing and Profitability Template
5.1 | Understanding the elements of cost for making and selling the product
5.2 | Guiding and helping in apportionment and allocation of Direct and Indirect costs
5.3 | Finalisation of Costing template
5.4 | Guiding on Process used to define the price of the products
5.5 | Finalisation of Pricing template
5.6 | Suggesting on areas (if any) where cost control can be done
5.7 | Template on Margin analysis- Actual v/s Standard
6 | Adhoc Points
6.1 | Strategy session on where to play and Finalisation on sales target
6.2 | Collection SOP

## Rezo ai-Vivek
Rezo ai |  | Business Consulting
S.No. | Interface / Tasks | October | November | December | January | Completed
1 | Baseline Assessment |  |  |  |  | Yet to complete
1.1 | Onboarding the client
1.2 | Discovery Visit Client place and understand client business, people, policies and processes
1.3 | Diagnostic Prepare a Diagnostic report based on the Discovery and share it with the client
1.4 | Design and implement management framework and MIS structure for all functions
2 | Business matrics, KPIs, KRAs MIS for business analysis
2.1 | measure and action for the key profitability, efficiency and liquidity ratios
2.2 | Strategy to Profitability
3 | Cash Flow forecasting and management
3.1 | Cash flow forecasting (to anticipate any potential shortfalls or surpluses)
3.2 | Template for Weekly and Monthly Cash flow forecasting and management
3.3 | Track the actual cash inflow and outflow against the forecasted no.
3.4 | Working Capital management
3.5 | Review the payment terms with vendor and suggest improvements
4 | Quarterly Business Review
4.1 | Preparation of MIS for 2 Quarters
4.2 | Review the performance with the management
5 | Strategic financial plan with well-defined business goals and Financial KPIs
5.1 | business goals and Financial KPIs
5.2 | Guiding and helping in apportionment and allocation of Direct and Indirect costs
5.3 | Define and implement Annual Operating plan (Annual Budget)
5.4 | Guiding on Process used to define the price of the products
5.5 | Finalisation of Pricing template
5.6 | Suggesting on areas (if any) where cost control can be done
5.7 | Template on Margin analysis- Actual v/s Standard
6 | Adhoc Points
6.1 | Strategy session on where to play and Finalisation on sales target
6.2 | Collection SOP
7 | Business partnering in all critical strategic & tactical decisions
7.1 | Actively participate as a CFO in fund raising, M &A deals and other critical projects

## Chennai FC
MONTHS
CLIENT NAME | FOCUS AREA | Sl.No. | TASK | OCT | NOV | DEC | JAN | FEB | MAR | Status Remarks
DAC DEVELOPERS | HR & Financial Baseline Assessment | 1 | Onboarding the client
DAC DEVELOPERS |  | 2 | Review and analyse existing Financials for growth tends and key financial ratios
DAC DEVELOPERS |  | 3 | Conduct the HR Baseline Assessment along with the HR Spoc and highlight the gap areas if any
DAC DEVELOPERS |  | 4 | Conduct the Finance baseline assessment along with Finance team and highlight gap areas if any
DAC DEVELOPERS |  | 5 | Review and analyse existing Financials for growth tends and key financial ratios
DAC DEVELOPERS
DAC DEVELOPERS | Business Diagnostics | 1 | Session with the founders on aspirations and the key challenges
DAC DEVELOPERS |  | 2 | Structured / Unstrucrured diagnostics on processes, challenges, issues in each function
DAC DEVELOPERS |  | 3 | Creating a buuiness diagnostics report and 180 days plan
DAC DEVELOPERS |  | 4 | Report Presentation to the founders
DAC DEVELOPERS
DAC DEVELOPERS | Cash Flow Forecasting & Management | 1 | Cash Flow forecasting and management | [6 empty] | Process Initated
DAC DEVELOPERS |  | 1.1 | Cash flow forecasting (to anticipate any potential shortfalls or surpluses) | [6 empty] | Process Initated
DAC DEVELOPERS |  | 1.2 | Template for Weekly and Monthly Cash flow forecasting and management | [6 empty] | Done
DAC DEVELOPERS |  | 1.2.1 | Track the actual cash inflow and outflow against the forecasted no. | [6 empty] | Process Initated
DAC DEVELOPERS |  | 1.2.2 | Align and Fix payment days for vendors, salary and reimbursement | [6 empty] | Process Initated
DAC DEVELOPERS |  | 1.2.2 | Receivable management through well defined follow up system and process | [6 empty] | Process Initated
DAC DEVELOPERS |  | 1.3 | Review the payment terms with vendor and suggest improvements | [6 empty] | Process Initated
DAC DEVELOPERS
DAC DEVELOPERS | Site processes and Control | 1 | Visit sites for evaluating process (Atleast 2-3 sites will be visited) | [6 empty] | Week Beginning 20th NOV
DAC DEVELOPERS |  | 1.1 | Evaluate all the necessary processes | [6 empty] | To be done
DAC DEVELOPERS |  | 1.2 | Evaluate inventory management and control in sites | [6 empty] | To be done
DAC DEVELOPERS |  | 1.2.1 | Evaluate segregations of duties at the site
DAC DEVELOPERS |  | 1.2.2 | Rescript, redefine processes, inventory control, segregation of duties and alignment with relevant functions
DAC DEVELOPERS |  | 1.3 | Aligning the management for the revised process
DAC DEVELOPERS |  | 1.4 | Implement the process
VADUVAMMAL | Finance Team | 1 | Recruitment & Induction to new Fin.Manager | [6 empty] | New Manager Joined Vaduvammal
VADUVAMMAL |  | 1.1 | Train the Finance manager and the team on monthly closing, provisioning etc | [6 empty] | Induction completed, Initiated Month Closing Process with the team
VADUVAMMAL |  | 1.2 | Re define and rotate job allocation among team | [6 empty] | Completed
VADUVAMMAL
VADUVAMMAL | Sales Planning, Execution & Review | 1 | Classification of Customers | [6 empty] | Initited
VADUVAMMAL |  | 1.1 | Finalize BOY Sales Plan | [6 empty] | Done
VADUVAMMAL |  | 1.2 | November Sales Plan | [6 empty] | Done
VADUVAMMAL |  | 1.2 | Establish Quarterly Rolling Plan | [6 empty] | To be Initiated
VADUVAMMAL |  | 2 | Establish Weekly/Monthly Reviews | [6 empty] | Initited
VADUVAMMAL |  | 2.1 | Establish the MIS for the weekly & monthly review | [6 empty] | Initited
VADUVAMMAL |  | 2.2 | Monthly MIS Compilation & Review with Management | [6 empty] | To be Initiated
VADUVAMMAL
VADUVAMMAL | Monthly P&L & Funds Flow Planning | 1 | Month Closing Process | [6 empty] | Initited
VADUVAMMAL |  | 1.1 | Monthly P&L Summary Compilation | [6 empty] | Initited
VADUVAMMAL |  | 1.2 | Monthly P&L Review | [6 empty] | Initited
VADUVAMMAL |  | 1.3 | Funds Flow Planning | [6 empty] | Initited
VADUVAMMAL
VADUVAMMAL | BOY Plan | 1 | Sales Plan for November 2023 to March 2024 | [6 empty] | Completed
VADUVAMMAL |  | 1.1 | P&L Forecase basis Sales Plan | [6 empty] | WIP
VADUVAMMAL |  | 1.2 | Over all Financials | [6 empty] | WIP
VC Nutri Foods | MIS Dashboard |  | Defining various dashboards required | [6 empty] | Completed
VC Nutri Foods |  |  | Input Data from Focus | [6 empty] | Done
VC Nutri Foods |  |  | Building Dashboards from Power BI Tools | [6 empty] | WIP
VC Nutri Foods |  |  | Reviewing the dashboards with VCNF Management | [6 empty] | Initial Output shared and reviewed with VCNF mgmt on 16th NOV
VC Nutri Foods |  |  | Finalize the Output Dashboards | [6 empty] | WIP
VC Nutri Foods
VC Nutri Foods | Sales Planning & Review | 1 | Monthly Sales Plan | [6 empty] | Initited
VC Nutri Foods |  | 1.1 | Weekly Sales Review | [6 empty] | Initited
VC Nutri Foods
VC Nutri Foods | Monthly P&L & Funds Flow Planning | 1 | Month Closing Process - Physical Verification process review | [6 empty] | Done, Production Order Confirmaton process implemented
VC Nutri Foods |  | 1.1 | Month Closing Process - PV Reconciliation Process | [6 empty] | To be Reviewed
VC Nutri Foods |  | 1.2 | Month Closing Process - Financial Closing | [6 empty] | To be Initiated, Discussed with management
VC Nutri Foods |  | 1.3 | Monthly P&L Summary Compilation | [6 empty] | To be Initiated
VC Nutri Foods |  | 1.4 | Monthly P&L Review | [6 empty] | To be Initiated
VC Nutri Foods |  | 1.5 | Funds Flow Planning | [6 empty] | Template shared with VCNF

## Pure Crop - Murali
Pure Crop - CFO Retainer
Focus Area | Sl No | Task | November |  |  |  | December | January
|  |  | Wk1 | Wk2 | Wk3 | Wk4
Pitch Deck revision | 1 | Changes in the Format & Content as per the client need, on going process.
Completed
Planned
In process
HR Related Requirements | 1 | Discussion Initiated regarding the requirements | [6 empty] | Delayed
| 2 | Execution as per the plan
Migration of Tally Data to Zoho | 1 | Discussion Initiated regarding the requirements
| 2 | Supervising Execution as per the plan

## Truckrr - BK
Truckrr (Ongoing Project Client)
Focus Area | Sl No | Task | October | November |  |  |  | December |  |  |  | Jan
|  |  |  | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4
FM & Pitch deck revision | 1 | Changes in the Format & Content as per the client need, on going process. | bar: November Wk1 to November Wk4
| 2 | [14 empty] | Completed
In process
Planned
ESOP | 1 | Initial level Discussions | [13 empty] | Delayed | bar: November Wk2
| 2 | Drafting & Preparation of ESOPs (Under Deepak Sir) | bar: November Wk3 to December Wk4
PVT Placements | 1 | Initial level Discussions
| 2 | Execution ( Under Deepak Sir) | bar: November Wk3 to December Wk4
Updated FM (Alternate) | 1 | Initial level Discussions | bar: December Wk4 to Jan Wk1
| 2 | Delievery of Updated FM | bar: November Wk3 to November Wk4; Jan Wk2

## Taurus
Business Consulting Agenda
Focus Area | Sl No | Task | December | January | February | March
Strategy Articulation and Integration | 1 | Discuss, brainstorm and finalize the winning aspiration for the strategy period
| 2 | Discuss, brainstorm and finalize the Go to market strategy i.e
| 3 | Where to play - Geography, Industry, Customer, channels etc
| 4 | How to win in the defined markets
| 5 | Discuss and define the capabilities required for winning - resources, funds, tools, technology etc
Product Business Model - Evaluation and Business Plan | 1 | Brainstorm on the strategy for all 3 products
| 2 | Formulate the business plans for ENECON,ENELYX,ALTEC
| 3 | Create a strategic financial plan for ENECON, ENELEX and ALTEC
| 4 | Sensitivity analysis, ROI, Payback period - evaluation and recommendation
Aligning Organization Structure and Role Expectations | 1 | Assess Organizational Goals and Needs, Review of "As Is" Org. Structure
| 2 | Propose the business appropriate structure: - Conduct the "Fit Tests" and "Good Design Tests" to ascertain the right structure.
| 3 | Define Reporting Relationships: - Determine the hierarchy of authority and reporting lines.
| 4 | Identify the Unique roles
Addittional Task - Management Routine | 1 | Design the Management Routine
| 2 | Creating structure of weekly/ Monthly review
| 3 | Creating Template to capture data
| 4 | Managers are inducted into the management routine process
| 5 | Rythym to weekly/monthly management routine commencement
Addittional Task - Market Area Planning | 1 | Designing the Market area planning as per new structure
| 2 | Developing the template
Strategic Financial Plan | 1 | Discuss and align on yearly targets for key financial deliverables i.e.
| 2 | Revenue and Gross margins targets for different markets, industry, customer, channels
| 3 | Direct costs and other fixed costs in terms of people, tools, technology, marketing, sales based on Org structure defined
| 4 | Evaluate and estimate the capex requirements
| 5 | Evaluate, estimate and optimize DSO, DPO and other working capital assumptions
| 6 | Evaluate funding requirements and define the appropriate capital structure - debt and equity
| 7 | Deliver the final financial plan
Annual Operating Plan | 1 | AOP launch, setting expectations, discussing key people involvement and finalizing the plan and calendar
| 2 | Sharing the formats, data requirement with different functions for data
| 4 | Receipt of details from Client's Team
| 5 | Preparation of AOP
Articulation of Business Critical Goals / KPIs | 1 | Identify business critical goals for each financial year in 4 categories : - financial goals, customer goals, business process goals and people development/ capability goals based on the strategy
| 2 | Identify the critical KPIs to be delivered against each of these goals
| 3 | Identify timelines for delivery of each of these goals
| 4 | Align the senior management and founders
| 5 | Make changes based on the discussion with the founders and senior management and start the implementation process
Quarterly Business Review | 1 | Define functional reviews and calendarize them
| 2 | Define the MIS And dashboards to be reviewed by each functions
| 3 | Create actionables and responsibilities out of review
| 4 | Evaluate next quarter's target and make changes if required
| 5 | Communicate the targets to the relevant functions
| 6 | Analyse and communicate the quarterly targets with all functions
Performance management | 1 | Designing Performance Management Framework (Including approach for current year appraisal)
| 2 | Goals Scripted for Leadership Team (Both What & How aspect of deliverables)
Monthly Performance Review | 1 | Performance of all functions for the month and YTD

## Taurus - BK (hidden)
Taurus
Focus Area | Sl No | Task | November |  |  |  | Dec |  |  |  | 2023-01-24
|  |  | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4
Diagonostic Done | 1 | Detailed Diagnostic Done | bar: November Wk1
| 2 | Diagnostic Report Provided | [12 empty] | Completed | bar: November Wk1
Planned
In process
Feasibility Analysis | 1 | Discuss, brainstorm and finalize the winning aspiration for the strategy period | [12 empty] | Delayed
| 2 | Discuss, brainstorm and finalize the Go to market strategy i.e
| 3 | Where to play - Geography, Industry, Customer, channels etc
| 4 | How to win in the defined markets
| 5 | Discuss and define the capabilities required for winning - resources, funds, tools, technology etc
Product Business Model - Evaluation and Business Plan | 1 | Brainstorm on the strategy for all 3 products
| 2 | Formulate the business plans for ENECON,ENELYX,ALTEC
| 3 | Create a strategic financial plan for ENECON, ENELEX and ALTEC
| 4 | Sensitivity analysis, ROI, Payback period - evaluation and recommendation
Strategic Financial Plan | 1 | Discuss and align on yearly targets for key financial deliverables i.e. | bar: November Wk2; 2023-01-24 Wk2 to 2023-01-24 Wk3
| 2 | Revenue and Gross margins targets for different markets, industry, customer, channels | bar: November Wk2; 2023-01-24 Wk2 to 2023-01-24 Wk3
| 3 | Direct costs and other fixed costs in terms of people, tools, technology, marketing, sales based on Org structure defined | bar: November Wk2; 2023-01-24 Wk4

## Maven - BK
Maven
Focus Area | Sl No | Task | November |  |  |  | Dec |  |  |  | 2023-01-24
|  |  | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4
Onboarding Session | 1 | Onboarding Session | bar: November Wk1; Dec Wk4
Completed | bar: November Wk1
Planned
In process
Structuring of MIS | 1 | Data Gathering | [12 empty] | Delayed | bar: 2023-01-24 Wk1
| 2 | Analysis of Data | bar: 2023-01-24 Wk2
| 3 | Structuring of MIS | bar: 2023-01-24 Wk3
Diagnostic | 1 | Diagnostic Session | bar: 2023-01-24 Wk1
| 2 | Detailed Diagnostic Report | bar: 2023-01-24 Wk2

## Saptham - BK (hidden)
Saptham - CFO retainer
Focus Area | Sl No | Task | November
|  |  | Wk1 | Wk2 | Wk3 | Wk4
Update FM | 1 | Changes in the Format & Content as per the client need, on going process.
Completed
In process
Planned
Sales & Marketing KPI | 1 | Initial KPI list sent to Sales & Marketing Head |  |  |  |  | Delayed
| 2 | Formulation of Sales strategy & KPIs in coordination with Sales head
| 3 | Identifying the Data Points needed & formulating the process of recording that properly.
| 4 | Rolling out the format & strategy points to be covered in Sales report from Sales head
| 5 | Evaluating the Sales report
Financial Control Process & KPI | 1 | Guiding the Accounts team to do proper month end closure
| 2 | Putting the proper control process in place in agreement with accounts team
| 3 | Following up with accounts team for access to monthly recs as listed.
| 4 | Reviewing the monthly closing numbers on high level basis.
Operations, Production, Quality Control KPI, new Product Strategy, Procurement | 1 | Initial KPI list Sent to Operations Head
| 2 | Formulation of KPIs in agreement with the Operations head
| 3 | Identifying the Data Points needed
| 4 | Rolling out the format & points to be covered in Operations report
| 5 | Evaluating the Sales report