## Sheet1
Focus Area | Tasks | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
Internal Process Diagnosis for Rewards and Recognition | Conduct in-depth interviews with HR leadership and key stakeholders
Review existing rewards and recognition policies and procedures
Analyze current performance evaluation metrics and their alignment with rewards
Assess the effectiveness of existing recognition programs
Identify gaps in current R&R processes
Benchmark against industry best practices
Develop recommendations for process improvements
Collaborate with IT to understand data availability and quality
Define key performance indicators (KPIs) for R&R dashboard
Create a detailed requirements document for dashboard functionalities
Review and approve dashboard mockups from a strategic HR perspective
Overview Dashboard | Define critical workforce metrics to be included
Determine appropriate data visualizations for each metric
Specify required drill-down capabilities for strategic analysis
Ensure alignment of dashboard with organizational goals
Review data integration plan to ensure all relevant HR data sources are included
Provide input on data normalization and standardization
Validate headcount metrics and definitions
Review and refine employee distribution categorizations
Ensure compliance with data privacy regulations
Conduct preliminary analysis using the dashboard to verify insights
Attrition Summary Dashboard | Define comprehensive attrition metrics (e.g., voluntary, involuntary, regrettable)
Specify required attrition trend analyses (e.g., by department, job level, tenure)
Determine appropriate benchmarks for attrition rates
Define 'at-risk' employee segments for proactive retention strategies
Ensure integration of exit interview data for qualitative insights
Review YTD movement calculations and visualizations
Validate attribute-based attrition breakdowns for accuracy and relevance
Provide input on predictive attrition modeling possibilities
Dynamic Pivot Chart | Identify key HR metrics for pivot analysis
Define relevant attribute combinations for strategic workforce planning
Specify required aggregation levels (e.g., department, location, job family)
Ensure pivot functionality aligns with common HR analysis needs
Review user interface for intuitive use by HR professionals
Playground / Tree Map | Define hierarchical structure for organizational data representation
Identify key metrics for size and color coding in tree map
Ensure tree map provides valuable insights for workforce composition analysis
Specify drill-down requirements for detailed workforce segment analysis
Deployment | Develop UAT scenarios based on typical HR analytical needs
Participate in UAT to ensure alignment with HR strategic requirements
Prioritize feedback based on impact on HR decision-making capabilities
Validate final adjustments meet strategic HR needs
Prepare change management plan for new analytics adoption
Documentation and Training | Review user documentation for completeness and relevance to HR users
Develop use cases and scenarios for training materials
Conduct executive-level presentations on dashboard capabilities
Gather feedback on potential strategic applications of the new analytics
Identify opportunities for advanced HR analytics initiatives