## Phase 3
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME |  |  | PROJECT MANAGER |  | PROJECT SPONSOR
Predictive Analytics Implementation - Phase 3 |  |  | Balasubramanian PG
EMAIL |  | PHONE | ORGANIZATIONAL UNIT(S)
GREEN BELTS ASSIGNED |  |  | EXPECTED START DATE |  | EXPECTED COMPLETION DATE
BLACK BELTS ASSIGNED |  |  | EXPECTED SAVINGS |  | ESTIMATED COSTS
|  |  | 0 |  | 0
PROJECT OVERVIEW
PROBLEM OR ISSUE | To implement predictive analytics for forecasting success factors, enabling the organization to make data-driven decisions for future growth and development.
PURPOSE OF PROJECT | • Develop and deploy predictive models to forecast success factors. • Integrate predictive analytics into organizational decision-making processes.
BUSINESS CASE | Motilal Oswal has internally developed an HRMS and seeks assistance in the generation and automation of various HR dashboards to facilitate decision-making. Additionally, they aim to streamline their success profiling assessment, which will be followed by the implementation of predictive analytics across certain HR dimensions.
GOALS / METRICS
EXPECTED DELIVERABLES | • Predictive models for forecasting success factors. • Documentation of model development and validation processes. • Integration plan for incorporating predictive analytics into business processes. • Training materials and sessions for stakeholders.
PROJECT SCOPE
WITHIN SCOPE | • Data collection and preparation for predictive modelling. • Development of predictive analytics models. • Validation and testing of models. • Integration of models into decision-making processes.
OUTSIDE OF SCOPE | • Detailed operational implementation beyond model deployment. • Ongoing monitoring and maintenance of predictive models.
TENTATIVE SCHEDULE
KEY MILESTONE |  |  | START |  | FINISH
Data collection and preparation
Development of predictive models
Validation and testing of models
Integration of models into business processes
Training for stakeholders
RESOURCES
PROJECT TEAM | Partner, Principal Consultant
SUPPORT RESOURCES | Subject Matter Expert Business Intelligence Consultant, HR Department, IT Support
SPECIAL NEEDS | Training Facilitators
COSTS
COST TYPE | VENDOR / LABOR NAMES |  | RATE | QTY | AMOUNT
Travelling |  |  |  | 0 | 0
Boarding and Lodging |  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Supplies |  |  |  | 0 | 0
Miscellaneous |  |  |  | 0 | 0
|  |  | TOTAL COSTS |  | 0
ESTIMATED TIME
Task ID | Task Description | Assigned To | Estimated Hours
1 | Data Collection and Preparation | HR Analysts | 40
2 | Identification of Profiles | HR Analysts | 60
3 | Patterns Analysis | Data Analysts | 80
4 | Report Preparation | HR Analysts | 40
5 | Presentation Development | Project Manager | 30
Total Estimated Hours |  |  | 250
BENEFITS AND CUSTOMERS
PROCESS OWNER | TBD
KEY STAKEHOLDERS | VP- Rewards and Comp, Senior Manager and Regional Manager-HR, BU Heads
FINAL CUSTOMER | TBD
EXPECTED BENEFITS | Lower attrition, Net positive Headcount, Streamlined L&D and Comp. processes.
TYPE OF BENEFIT | BASIS OF ESTIMATE |  |  |  | ESTIMATED BENEFIT AMOUNT
Lower attrition |  |  |  |  | 0
Net positive Headcount |  |  |  |  | 0
Streamlined L&D and Comp. processes |  |  |  |  | 0
0
0
0
0
|  |  | TOTAL BENEFIT |  | 0
RISKS, CONSTRAINTS, AND ASSUMPTIONS
RISKS | • Data quality and completeness issues. • Resistance to change from stakeholders. • Technical challenges in integrating models with existing systems.
CONSTRAINTS | • Limited budget for advanced analytics tools. • Time constraints for developing and validating models.
ASSUMPTIONS | • Availability of high-quality data for model development. • Cooperation from departments for data collection and validation.
Additional Information
Given the complexity and criticality of this project, regular status updates, milestone reviews, and risk assessments will be conducted to ensure project success. Continuous collaboration and feedback from stakeholders will be encouraged to address any emerging challenges effectively.
PREPARED BY | TITLE |  |  |  | DATE
IMPORTANT REMINDER
A narrative written charter must be circulated and signed by the project sponsors. You can attach a completed version of this template to your narrative written charter in an effort to keep it short and concise.
Please make sure you meet with the project team and sponsors before completing this template. Much of the information required will need to come from a discussion with team members and sponsors.

## Phase 2
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME |  |  | PROJECT MANAGER |  | PROJECT SPONSOR
Enhanced Reporting and MIS Implementation - Phase 2 |  |  | Abhimanyu Kumar
EMAIL |  | PHONE | ORGANIZATIONAL UNIT(S)
GREEN BELTS ASSIGNED |  |  | EXPECTED START DATE |  | EXPECTED COMPLETION DATE
BLACK BELTS ASSIGNED |  |  | EXPECTED SAVINGS |  | ESTIMATED COSTS
|  |  | 0 |  | 0
PROJECT OVERVIEW
PROBLEM OR ISSUE | To identify and analyze successful profiles within the organization to understand the factors contributing to their success.
PURPOSE OF PROJECT | • Identify successful profiles within the organization. • Analyze patterns among successful profiles to uncover common factors contributing to success.
BUSINESS CASE | Motilal Oswal has internally developed an HRMS and seeks assistance in the generation and automation of various HR dashboards to facilitate decision-making. Additionally, they aim to streamline their success profiling assessment, which will be followed by the implementation of predictive analytics across certain HR dimensions.
GOALS / METRICS
EXPECTED DELIVERABLES | • Comprehensive report on successful profiles and patterns analysis. • Presentation summarizing key findings and recommendations.
PROJECT SCOPE
WITHIN SCOPE | • Identification of successful profiles across different departments or teams. • Analysis of key attributes, skills, and behaviors of successful profiles.
OUTSIDE OF SCOPE | • Detailed performance evaluations or individual performance assessments. • Implementation of specific interventions based on the analysis.
TENTATIVE SCHEDULE
KEY MILESTONE |  |  | START |  | FINISH
Data collection and preparation |  |  | 2024-05-13 |  | 2024-05-17
Identification of successful profiles |  |  | 2024-05-20 |  | 2024-05-24
Analysis of patterns among successful profiles |  |  | 2024-05-20 |  | 2024-05-24
Report preparation |  |  | 2024-05-27 |  | 2024-05-31
Report preparation |  |  | 2024-05-27 |  | 2024-05-31
RESOURCES
PROJECT TEAM | Partner, Principal Consultant
SUPPORT RESOURCES | Subject Matter Expert Business Intelligence Consultant, HR Department, IT Support
SPECIAL NEEDS | Training Facilitators
COSTS
COST TYPE | VENDOR / LABOR NAMES |  | RATE | QTY | AMOUNT
Travelling |  |  |  | 0 | 0
Boarding and Lodging |  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Supplies |  |  |  | 0 | 0
Miscellaneous |  |  |  | 0 | 0
|  |  | TOTAL COSTS |  | 0
ESTIMATED TIME
Task ID | Task Description | Assigned To | Estimated Hours
1 | Data Collection and Preparation | Data Scientists | 50
2 | Model Development | Data Scientists | 100
3 | Model Validation and Testing | Data Scientists | 60
4 | Integration Planning | IT Support | 40
5 | Training and Documentation | Training Facilitators | 30
Total Estimated Hours |  |  | 280
BENEFITS AND CUSTOMERS
PROCESS OWNER | TBD
KEY STAKEHOLDERS | VP- Rewards and Comp, Senior Manager and Regional Manager-HR, BU Heads
FINAL CUSTOMER | TBD
EXPECTED BENEFITS | Lower attrition, Net positive Headcount, Streamlined L&D and Comp. processes.
TYPE OF BENEFIT | BASIS OF ESTIMATE |  |  |  | ESTIMATED BENEFIT AMOUNT
Lower attrition |  |  |  |  | 0
Net positive Headcount |  |  |  |  | 0
Streamlined L&D and Comp. processes |  |  |  |  | 0
0
0
0
0
|  |  | TOTAL BENEFIT |  | 0
RISKS, CONSTRAINTS, AND ASSUMPTIONS
RISKS | • Potential reluctance or resistance from employees to participate in the analysis. • Data quality issues affecting the accuracy of analysis results. • Time constraints impacting the depth of analysis.
CONSTRAINTS | • Limited availability of historical data for analysis. • Confidentiality and privacy concerns regarding employee data.
ASSUMPTIONS | • Access to relevant data and information about employee performance and attributes. • Cooperation and participation of employees in surveys or interviews.
Additional Information
Given the complexity and criticality of this project, regular status updates, milestone reviews, and risk assessments will be conducted to ensure project success. Continuous collaboration and feedback from stakeholders will be encouraged to address any emerging challenges effectively.
PREPARED BY | TITLE |  |  |  | DATE
IMPORTANT REMINDER
A narrative written charter must be circulated and signed by the project sponsors. You can attach a completed version of this template to your narrative written charter in an effort to keep it short and concise.
Please make sure you meet with the project team and sponsors before completing this template. Much of the information required will need to come from a discussion with team members and sponsors.

## EXAMPLE - Project Charter
PROJECT CHARTER TEMPLATE WITH EXAMPLE DATA
GENERAL PROJECT INFORMATION
PROJECT NAME |  |  | PROJECT MANAGER |  | PROJECT SPONSOR
Positive Charge EMV Station Installations |  |  | Jane Matthews |  | Jill DeGrassio
EMAIL |  | PHONE | ORGANIZATIONAL UNIT(S)
jane.matthews@positivecharge.com |  | 000-000-0000 | Field Engineering, Operations, and Project Management
GREEN BELTS ASSIGNED |  |  | EXPECTED START DATE |  | EXPECTED COMPLETION DATE
Wendy Williams (Project Management) |  |  | 2/19/20XX |  | 11/30/20XX
BLACK BELTS ASSIGNED |  |  | EXPECTED SAVINGS |  | ESTIMATED COSTS
Rakesh Agarwal (Director of Operations) |  |  | 237750 |  | 441855
PROJECT OVERVIEW
PROBLEM OR ISSUE | Our goal for this project is to install 1,125 EV charging stations at 116 locations across the US, Mexico and Canada to accommodate malls' and service stations' EV-charging needs.
PURPOSE OF PROJECT | The implementation of the 1,125 EV charging stations will reduce fossil-fuel emissions, and have a positive impact on the environment. This will help fulfill Positive Charge's mission of being the world's largest EV-charging provider and reduce the environmental impact of fossil-fuel cars through our services.
BUSINESS CASE | As EVs become more prevalent, more EV-charging stations are needed to accommodate EV drivers' charging needs. The implementation of the 1,125 EV charging stations at 116 locations across the US, Mexico, and Canada to accommodate malls' and service stations' EV-charging "traffic" will reduce the lengths to which EV drivers would have to travel for their next charge. The implementation of the EV-charging stations will also result in a 24% profit for Positive Charge.
GOALS / METRICS | The project goal is to install 1,125 EV charging stations at 116 locations across the US, Mexico and Canada. The metrics used to measure success will primarily be the following key performance indicators (KPIs): Revenue Growth, Client Retention Rate, and Customer Satisfaction.
EXPECTED DELIVERABLES | Install 1,125 EV charging stations at 116 locations across the US, Mexico and Canada to accommodate malls' and service stations' EV-charging needs.
PROJECT SCOPE
WITHIN SCOPE | Operations engineers, project managers and field implementation engineers will work with third-party client site personnel to install 1,125 EV charging stations at 116 locations across the US, Mexico and Canada.
OUTSIDE OF SCOPE | Positive Charge is not responsible for third-party / clients locations preparatory work (e.g., permits for digging, city region electricity-availability logistics, etc.). However, Positive Charge project managers can provide clients with a checklist to ensure their locations are adequately prepared for the installation of our EV charging stations.
TENTATIVE SCHEDULE
KEY MILESTONE |  |  | START |  | FINISH
Form Project Team / Preliminary Review / Scope |  |  | 12/05/20XX |  | 01/11/20XX
Finalize Project Plan / Charter / Kick Off |  |  | 12/06/20XX |  | 02/01/20XX
Define Phase |  |  | 12/07/20XX |  | 02/02/20XX
Measurement Phase |  |  | 12/08/20XX |  | 02/10/20XX
Analysis Phase |  |  | 12/09/20XX |  | 02/26/20XX
Improvement Phase |  |  | 01/10/20XX |  | 03/10/20XX
Control Phase |  |  | 02/08/20XX |  | 03/08/20XX
Project Summary Report and Close Out |  |  | 04/23/20XX |  | 06/23/20XX
RESOURCES
PROJECT TEAM | Janine Remagio - Project Manager David Coen - Chief Engineer Rita Preze - CFO |  | Lisa Jones - QA Director Donald Smythe - Field Engineer
SUPPORT RESOURCES | Operations, Sales, Project Management, Engineering
SPECIAL NEEDS | TBD
COSTS
COST TYPE | VENDOR / LABOR NAMES |  | RATE | QTY | AMOUNT
Labor | Electro Charge Logistics, Inc. |  | 78 | 200 | 15600
Labor | Level 1 EVS |  | 46 | 100 | 4600
Labor | Level 2 EVS |  | 58 | 50 | 2900
Labor | EVC Fast Chargers |  | 85000 | 1 | 85000
Labor | Battery Vendor |  | 79879 | 3 | 239637
Supplies | Power Conversion System Vendor |  | 68686 | 1 | 68686
Miscellaneous | Third-Party Software |  | 25432 | 1 | 25432
|  |  | TOTAL COSTS |  | 441855
BENEFITS AND CUSTOMERS
PROCESS OWNER | Jane Matthews - Project Manager
KEY STAKEHOLDERS | Jill DeGrassio
FINAL CUSTOMER | 116 clients across the US, Mexico and Canada (see attached client list).
EXPECTED BENEFITS | The implementation of the 1,125 EV charging stations at 116 locations across the US, Mexico and Canada to accommodate malls' and service stations' EV-charging "traffic" will reduce the lengths to which EV drivers would have to trave for their next charge. The implementation of the EV-charging stations will also result in a 24% profit for Positive Charge.
TYPE OF BENEFIT | BASIS OF ESTIMATE |  |  |  | ESTIMATED BENEFIT AMOUNT
Specific Cost Savings | Estimator's projections |  |  |  | 25000
Enhanced Revenues | Finance's projections |  |  |  | 92500
Higher Productivity (Soft) | Project management's estimations |  |  |  | 17500
Improved Compliance | Operations' estimations |  |  |  | 12000
Better Decision Making | Project management's estimations |  |  |  | 18500
Less Maintenance | Project management's estimations |  |  |  | 26000
Other Costs Avoided | Finance's projections |  |  |  | 46250
|  |  | TOTAL BENEFIT |  | 237750
RISKS, CONSTRAINTS, AND ASSUMPTIONS
RISKS | Though contract is signed, Operations still does not have approval for installation from cities of Denver and Yuma. Project management to work with both cities to ensure proper permitting, etc. in time for scheduled installations.
CONSTRAINTS | We have to "backfill" some key project management and field engineer positions to ensure we have people "on the ground" to manage EV stations' implementation.
ASSUMPTIONS | We assume that all permits for installation of EV-charging stations will be provided by clients by time of implementation.
PREPARED BY | TITLE |  |  |  | DATE
Jane Matthews | Senior Project Manager |  |  |  | 04/22/20XX
CLICK HERE TO CREATE IN SMARTSHEET
IMPORTANT REMINDER
A narrative written charter must be circulated and signed by the project sponsors. You can attach a completed version of this template to your narrative written charter in an effort to keep it short and concise.
Please make sure you meet with the project team and sponsors before completing this template. Much of the information required will need to come from a discussion with team members and sponsors.

## Phase 1
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME |  |  | PROJECT MANAGER |  | PROJECT SPONSOR
Enhanced Reporting and MIS Implementation - Phase 1 |  |  | Balasubramanian PG
EMAIL |  | PHONE | ORGANIZATIONAL UNIT(S)
GREEN BELTS ASSIGNED |  |  | EXPECTED START DATE |  | EXPECTED COMPLETION DATE
BLACK BELTS ASSIGNED |  |  | EXPECTED SAVINGS |  | ESTIMATED COSTS
|  |  | 0 |  | 0
PROJECT OVERVIEW
PROBLEM OR ISSUE | To develop enhanced reporting dashboards and automate the generation of MIS reports, ensuring timely and accurate information for decision-making processes.
PURPOSE OF PROJECT | • Develop and implement enhanced reporting dashboards for recruiting, talent management, and market-led metrics. • Automate the generation of MIS reports with scheduled refreshes.
BUSINESS CASE | Motilal Oswal has internally developed an HRMS and seeks assistance in the generation and automation of various HR dashboards to facilitate decision-making. Additionally, they aim to streamline their success profiling assessment, which will be followed by the implementation of predictive analytics across certain HR dimensions.
GOALS / METRICS
EXPECTED DELIVERABLES | • Enhanced reporting dashboards for recruiting, talent management, and market-led metrics. • Automated MIS report generation system with scheduled refresh capabilities. • Documentation and user guides for the new dashboards and automation processes. • Training sessions for key stakeholders •Implementation of predictive analytics to forecast success factors.
PROJECT SCOPE
WITHIN SCOPE | • Development of recruiting, talent management, and market-led metrics dashboards. • Automation of report generation for these dashboards. • Integration with existing data sources and systems.
OUTSIDE OF SCOPE | • Manual data entry and reporting processes. • Customization beyond initial dashboard requirements.
TENTATIVE SCHEDULE
KEY MILESTONE |  |  | START |  | FINISH
Requirement gathering and analysis |  |  | 2024-06-01 |  | 2024-06-05
Dashboard development |  |  | 2024-06-16 |  | 2024-06-20
Automation setup |  |  | 2024-06-16 |  | 2024-06-20
Testing and validation |  |  | 2024-06-24 |  | 2024-06-28
User training and documentation |  |  | 2024-06-24 |  | 2024-06-28
RESOURCES
PROJECT TEAM | Partner, Principal Consultant
SUPPORT RESOURCES | Subject Matter Expert Business Intelligence Consultant, HR Department, IT Support
SPECIAL NEEDS | Training Facilitators
COSTS
COST TYPE | VENDOR / LABOR NAMES |  | RATE | QTY | AMOUNT
Travelling |  |  |  | 0 | 0
Boarding and Lodging |  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Supplies |  |  |  | 0 | 0
Miscellaneous |  |  |  | 0 | 0
|  |  | TOTAL COSTS |  | 0
ESTIMATED TIME
Task ID | Task Description | Assigned To | Estimated Hours
1 | Requirement Gathering and Analysis | Project Manager, HR Analysts | 40
2 | Dashboard Development | Data Analysts | 90
3 | Automation Setup | IT Support | 60
4 | Testing and Validation | Data Analysts, IT Support | 50
5 | Training and Documentation | Training Facilitators | 20
Total Estimated Hours |  |  | 260
BENEFITS AND CUSTOMERS
PROCESS OWNER | TBD
KEY STAKEHOLDERS | VP- Rewards and Comp, Senior Manager and Regional Manager-HR, BU Heads
FINAL CUSTOMER | TBD
EXPECTED BENEFITS | Lower attrition, Net positive Headcount, Streamlined L&D and Comp. processes.
TYPE OF BENEFIT | BASIS OF ESTIMATE |  |  |  | ESTIMATED BENEFIT AMOUNT
Lower attrition |  |  |  |  | 0
Net positive Headcount |  |  |  |  | 0
Streamlined L&D and Comp. processes |  |  |  |  | 0
0
0
0
0
|  |  | TOTAL BENEFIT |  | 0
RISKS, CONSTRAINTS, AND ASSUMPTIONS
RISKS | • Potential reluctance or resistance from employees to participate in the analysis. • Data quality issues affecting the accuracy of analysis results. • Time constraints impacting the depth of analysis.
CONSTRAINTS | • Limited availability of historical data for analysis. • Confidentiality and privacy concerns regarding employee data.
ASSUMPTIONS | • Access to relevant data and information about employee performance and attributes. • Cooperation and participation of employees in surveys or interviews.
Additional Information
Given the complexity and criticality of this project, regular status updates, milestone reviews, and risk assessments will be conducted to ensure project success. Continuous collaboration and feedback from stakeholders will be encouraged to address any emerging challenges effectively.
PREPARED BY | TITLE |  |  |  | DATE
IMPORTANT REMINDER
A narrative written charter must be circulated and signed by the project sponsors. You can attach a completed version of this template to your narrative written charter in an effort to keep it short and concise.
Please make sure you meet with the project team and sponsors before completing this template. Much of the information required will need to come from a discussion with team members and sponsors.

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.